## Overview
Business Incubation Center
Sr# | Code | Group | Strategic Projects | Timeline
1 | BICP1 | EEC | Enhance Entrpreneural Capacity | 2022-23
2 | BICP2 | INS | Increase number of Startups | 2023-2024
3 | BICP3 | IBI | Increase BIC Infrastructure | 2024-2025
4 | BICP4

## Instructions
Strategic Plan Implementation Cell (SPIC)
Departmental Action Plan
Preperational Guide Lines
step 1 | Overview | This sheet defines the overall projects for a particular department / constituent unit
This is divided into the following columns
|  | Sr# | Code | Group | Strategic Projects and Tasks | Timeline
|  | serial no. | dept + project no. | project abbreviation | orderly breakdown of sub projects/ tasks | expected execution
|  | 1 | BICP1 | EEC | Enhance Entrpreneural Capacity | 2022-23 | PROJECT | target area in strategic plan
step 2 | Overview | Each key target i.e. PROJECT will be broken down into sub project (SP)/ tasks for better understanding and execution
|  | 1 | BICP1 | EEC | Enhance Entrpreneural Capacity | 2022-23 | PROJECT
|  | 1.1 |  | SP1 | SIYB Training on Entreprenuership |  | SUB-PROJECT | Breakdown of the Project
|  | 1.2 |  | SP2 | SIYB Training of Trainers
|  | 1.3 |  | SP3 | Faculty Engagement Workshops
|  | 1.4 |  | SP4 | Liaison with Chamber of Commerces
Step 3 | Project Breakdown | Each project will be broken down into sub projects which will further be divided into tasks and timeline
|  | 1 | BICP1 | EEC | Enhance Entrpreneural Capacity |  |  |  | PROJECT
|  | 1.1 |  | SP1 | SIYB Training on Entreprenuership | Start | End | Status | SUB-PROJECT
|  | 1.1.1 |  | Task | Required Approvals | 2022-03-10 | 2022-03-20 | 100%
|  | 1.1.2 |  |  | Finalization of Training Venue & Schedule | 2022-03-21 | 2022-03-28 | 50% | TASKS
|  | 1.1.3 |  |  | Awareness Campaigns | 2022-04-08 | 2022-04-21 | 50%
step 4 | Other sub project breakdowns |  | Repeat step 3 (SP onwards) for the further sub projects in a particular project
| New project |  | create a new sheet and follow step 3 from the start

## P1_EEC
Sr# | Code | Group | Strategic Projects and Tasks | Timeline
1 | BICP1 | EEC | Enhance Entrpreneural Capacity |  |  | target area in strategic plan | PROJECT
1.1 |  | SP1 | SIYB Training Of Entrepreneurs | Start | End | strategies on how to achieve the target | SUB-PROJECT
1.1.1 |  | TASK | Required Approvals | 2022-03-10 | 2022-03-20
1.1.2 |  |  | Finalization of Training Venue & Schedule | 2022-03-21 | 2022-03-28
1.1.3 |  |  | Awareness Campaigns | 2022-04-08 | 2022-04-21
1.1.4 |  |  | Call For Application & Registration Process | 2022-04-22 | 2022-05-05 | actions to be taken
1.1.5 |  |  | Procurement of Training Material | 2022-04-25 | 2022-05-08
1.1.6 |  |  | Exection of Training | 2022-05-10 | 2022-05-16
1.1.7 |  |  | M&E And Closure of Training (certificate distribution) | 2022-05-17 | 2022-05-17
1.2 |  | SP2 | SIYB Training Of Trainers |  |  | strategies on how to achieve the target | SUB-PROJECT
1.2.1 |  | TASK | Required Approvals | 2022-06-10 | 2022-07-20
1.2.2 |  |  | Finalization of Training Venue & Schedule | 2022-06-10 | 2022-07-20
1.2.3 |  |  | Awareness Campaigns | 2022-07-21 | 2022-07-31
1.2.4 |  |  | Call For Application & Registration Process | 2022-07-25 | 2022-08-10
1.2.5 |  |  | Procurement of Training Material | 2022-07-25 | 2022-08-10
1.2.6 |  |  | Exection of Training | 2022-08-15 | 2022-08-26
1.2.7 |  |  | M&E And Closure of Training (Certificate Distribution) | 2022-08-27 | 2022-08-31
1.3 |  | SP3 | Engagement Workshops |  |  |  | SUB-PROJECT
1.3.1 |  | TASK | Identify the resource person to be engaged | 2022-09-10 | 2022-09-20
1.3.2 |  |  | identify the workshop theme and resource persons | 2022-09-10 | 2022-09-20
1.3.3 |  |  | Required Approvals | 2022-09-10 | 2022-09-20
1.3.4 |  |  | Finalization of Venue & Schedule | 2022-09-21 | 2022-09-27
1.3.5 |  |  | Nominations of participants | 2022-09-21 | 2022-09-27
1.3.6 |  |  | Exection of Workshop | 2022-09-28 | 2022-09-29
1.3.7 |  |  | M&E And Closure | 2022-10-02 | 2022-10-04
1.4 |  | SP4 | Liaison with Chamber of Commerces
IIUI signed an MOU with ICCI
1.4.1 |  | TASK | Propose to ICCI for Activity | 2022-09-10 | 2022-09-20
1.4.2 |  |  | Confirmation from ICCI | 2022-09-10 | 2022-10-10
1.4.3 |  |  | Seek program approval from higher authorities | 2022-10-11 | 2022-10-24
1.4.4 |  |  | Identify the industry (to seek active problems for R&D and commercialisation) | 2022-10-25 | 2022-11-04
1.4.5 |  |  | Departmental nominations for he Activity | 2022-11-01 | 2022-11-11
1.4.6 |  |  | Execution of the Activity | 2022-11-21 | 2022-12-30
1.4.7 |  |  | M&E / reporting | 2023-01-02 | 2023-01-13
1.5 |  | SP5 | Activity
1.5.1 |  | TASK | Approval from higher authority | 2022-09-12 | 2022-09-16
1.5.2 |  |  | Identification and Liaison with relevant department | 2022-09-17 | 2022-09-23
1.5.3 |  |  | Finalization of Schedule | 2022-09-17 | 2022-09-23
1.5.4 |  |  | Awareness session/ marketing/ registrations | 2022-09-24 | 2022-10-07
1.5.5 |  |  | Activity | 2022-09-24 | 2022-10-07
1.5.6 |  |  | Activity | 2022-10-10 | 2022-10-13
1.5.7 |  |  | Execution and Completion | 2022-10-18 | 2022-10-20
1.6 |  | SP6 | SIYB Training Of Entrepreneurs | Start | End
1.6.1 |  | TASK | Required Approvals | 2022-03-10 | 2023-03-20
1.6.2 |  |  | Finalization of Training Venue & Schedule | 2022-03-21 | 2023-03-28
1.6.3 |  |  | Awareness Campaigns | 2022-04-08 | 2023-04-21
1.6.4 |  |  | Call For Application & Registration Process | 2022-04-22 | 2023-05-05
1.6.5 |  |  | Procurement of Training Material | 2022-04-25 | 2023-05-08
1.6.6 |  |  | Exection of Training | 2022-05-10 | 2023-05-16
1.6.7 |  |  | M&E And Closure of Training (certificate distribution) | 2022-05-17 | 2023-05-17
1.7 |  | SP7 | SIYB Training Of Trainers
1.7.1 |  | TASK | Required Approvals | 2022-06-10 | 2023-07-20
1.7.2 |  |  | Finalization of Training Venue & Schedule | 2022-06-10 | 2023-07-20
1.7.3 |  |  | Awareness Campaigns | 2022-07-21 | 2023-07-31
1.7.4 |  |  | Call For Application & Registration Process | 2022-07-25 | 2023-08-10
1.7.5 |  |  | Procurement of Training Material | 2022-07-25 | 2023-08-10
1.7.6 |  |  | Exection of Training | 2022-08-15 | 2023-08-26
1.7.7 |  |  | M&E And Closure of Training (Certificate Distribution) | 2022-08-27 | 2023-08-31

## P2_INS
Sr# | Code | Group | Strategic Projects and Tasks | Timeline
2 | BICP2 | INS | Increase Number of Startup
2.1 |  | SP1 | Induction of Startups | Start | End
2.1.1 |  | TASK | Startup Application Process | 2022 | 2025
2.1.2 |  |  | open call for new startups
2.1.3 |  |  | Compile Applications and Call SARC meeting
2.1.4 |  |  | Conduct SARC meeting and compile results
2.1.5 |  |  | Inform the selected applications to incubate their startup
2.1.6 |  |  | Lease agreement signed and approved
2.2 |  | SP2 | Funding Opportunties For Startups and Linkages with Investors
2.2.1 |  |  | Identifying and sharing grant opportunities/ competitions with startups | on going
2.2.2 |  |  | Liaison with ICCI/ICSTSI and potential investors/industry | on going
2.2.3 |  |  | Developing a multiskilled pool of internal and external mentors | on going
2.3 |  | SP3 | Sub_Project
2.3.1 |  |  | Task1
2.3.2 |  |  | Task2
2.4 |  | SP4 | Sub_Project
2.4.1 |  |  | Obtain Required Approvals
2.4.2 |  |  | Allocation of budget
2.4.3 |  |  | Task1
2.4.4 |  |  | Task2
2.5 |  | SP5 | Virtual Incubation of Entrepreneurs
2.5.1 |  |  | Obtain required approvals
2.5.2 |  |  | Task1
2.5.3 |  |  | Task2
2.5.4 |  |  | Task3
2.5.5 |  |  | Task4
2.6 |  | SP6 | Sub_Project
2.6.1 |  |  | Obtain Required Approvals
2.6.2 |  |  | Task1
2.6.3 |  |  | Task2
2.6.4 |  |  | Task3
2.7 |  | SP7 | Sub_Project
2.7.1 |  |  | Obtain Required Approval
2.7.2 |  |  | Task1
2.7.3 |  |  | Task2
2.7.4 |  |  | Task3
2.7.5 |  |  | Task4
2.7.6 |  |  | Task5
2.8 |  | SP8 | Sub_Project
2.8.1 |  |  | Obtain Required Approvals
2.8.2 |  |  | Task1
2.8.3 |  |  | Task2
2.8.4 |  |  | Task3
2.9 |  | SP9 | Sub_Project
2.9.1 |  |  | Obtain Required Approval
2.9.2 |  |  | Task1
2.9.3 |  |  | Task2
2.9.4 |  |  | Task3
2.9.5 |  |  | Task4
2.9.6 |  |  | Task5
2.1 |  | SP10 | Sub_Project
2.10.1 |  |  | Prepare Model
2.10.2 |  |  | Obtain Required Approval
2.10.3 |  |  | Implement Model

## P3_IBI
Sr# | Code | Group | Strategic Projects and Tasks | Timeline
3 | BICP3 | IBI | Increase BIC Infrastructure | Start | End
3.1 |  | SP1 | Identification of space | 2025 | 2026
3.1.1 |  |  | Task1
3.1.2 |  |  | Task2
3.1.3 |  |  | Task3
3.2 |  | SP2 | XYZ
3.2.1 |  |  | Task1
3.2.2 |  |  | Task2
3.2.3 |  |  | Task3